**Communications regarding UCAR RFP R15-19374 (NWSC-2)**

Revision History:

Revision #1: 14 May 2015

Table of Contents

[1 Overview 1](#_Toc419287552)

[1.1 Conventions 1](#_Toc419287553)

[2 Amendment #1, 14 May 2015 2](#_Toc419287554)

[2.1 Modification to the NWSC-2 RFP document 2](#_Toc419287555)

[2.1.1 Change to Section 2.1, Proposal Due Date and Time 2](#_Toc419287556)

[2.1.2 Change to Section 2.21, Schedule 2](#_Toc419287557)

# Overview

Amendments to UCAR RFP R15-19374 (NWSC-2) subsequent to its release on Friday, 3 April 2015, are issued through annotated revisions of the affected RFP document(s). This document is used to compile all changes made and to provide an explanation of those changes. This document will be revised and reposted to the NWSC-2 website (<https://www2.cisl.ucar.edu/NWSC-2>) as often as necessary. UCAR will inform registered Offerors of updates, but Offerors should also periodically check the website for new updates.

## Conventions

Each Amendment is numbered sequentially and all changes to the RFP documents are annotated as follows.

* All changes are made in red.
* Each modification is annotated with an amendment version number tag in square brackets. For example: [A1] precedes changes introduced in Amendment 1 of the RFP; [A2] precedes changes introduced in Amendment 2 of the RFP, and so forth.
* Deletions are shown in red-strikethrough, e.g.: ~~this has been deleted~~
* Insertions are shown in red, e.g. this has been inserted

An example of a change, the insertion of “brown” and correction of the second “fox”, follows:

The quick [A1] brown fox jumped over the lazy [A1] ~~fox~~ dog.

# Amendment #1, 14 May 2015

The following sections summarize the changes made to UCAR RFP R15-19374 (NWSC-2) between its release on 3 April 2015 and this amendment (Amendment #1), issued 14 May 2015.

## Modification to the NWSC-2 RFP document

The following modifications have been made to create file **UCAR RFP R15-19374 NWSC-2 v2.docx**.

### Change to Section 2.1, Proposal Due Date and Time

This section is changed to read as follows:

Firm fixed price proposals are due no later than 15:00 MDT on [A1] ~~Tuesday, 19~~ Friday, 29 May 2015.

### Change to Section 2.21, Schedule

The table is changed as follows:

|  |  |  |
| --- | --- | --- |
| Milestone | Day | Date |
| NWSC 2 RFP issue date | Fri. | 3 April 2015 |
| NWSC-2 RFP questions due to UCAR | Wed., 15:00 MDT | 22 April 2015 |
| UCAR response to RFP questions distributed to Offerors | Wed. | 29 April 2015 |
| Proposals due to UCAR | [A1] ~~Tue~~ Fri., 15:00 MDT | [A1] ~~19~~ 29 May 2015 |
| Clarification Question Period | - | May/June 2015 |
| Evaluation of proposals completed | - | July 2015 |
| Negotiations concluded | - | August 2015 |
| Subcontract award | - | September 2015 |
| Project management meetings, installation planning, pre-delivery testing | - | October 2015 through June 2016 |
| Test systems delivery/installation | - | IPEDD minus 30-60 days |
| AMPS system delivery/installation | - | To be negotiated |
| Initial production equipment delivery date | - | IPEDD (TBD) |
| Installation of initial equipment complete | - | October 2016 |
| Acceptance of initial equipment | - | End December 2016 |